## Master List
Master Project Task List
Task | Phase | Team Lead | Due Date | Progress | Notes
Kickoff & Meeting Minutes | Phase 1: Project Setup and Qualitative Research | Team | 2024-01-29 | Complete
Project Management Plan | Phase 1: Project Setup and Qualitative Research | Jarred & Kathleen | 2024-01-29 | Complete
Project Schedule: Gant Chart | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete
Project Setup: Github Repo | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-01-29 | Complete
Research & Summary: Boone 2030 Plan | Phase 1: Project Setup and Qualitative Research | Jingyi | 2024-02-12 | In Progress
Research & Summary: Development Ordinances | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | In Progress
Research & Summary: Demographics | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-02-12 | In Progress
Research & Summary: Socio-economic Change | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | In Progress
Research & Summary: Story of Affordability | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | In Progress
Research & Summary:NC LIHTC Allocation Plan | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | In Progress
Research & Summary: "Workforce" Housing Programs | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | In Progress
Gather Open Data | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | In Progress
Update Readme with progress (week1-3) | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete
Update Presentation Slides (week1-3) | Phase 1: Project Setup and Qualitative Research | Jingyi & Yinan | 2024-01-29 | Complete
Chris Quattro Meeting & Minutes | Phase 2: Data Wrangling & Exploratory Analysis | Team | 2024-02-13 | In Progress
Data Wrangling: Septic Permit Web Scraping | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12 | In Progress
Data Wrangling: Physiucal Landscape | Phase 2: Data Wrangling & Exploratory Analysis | Jingyi | 2024-02-12 | In Progress
Data Wrangling: Municipal & Legal Lines | Phase 2: Data Wrangling & Exploratory Analysis | Jarred | 2024-02-12 | In Progress
Data Wrangling: Inventory of Built Environment | Phase 2: Data Wrangling & Exploratory Analysis | Alice | 2024-02-12 | In Progress
Data Wrangling: Demographics | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen |  | In Progress
Use Case & Exploratory Analysis Write Up | Phase 2: Data Wrangling & Exploratory Analysis | Jarred & Kathleen | 2024-02-12 | Not Started
Gather Open Data | Phase 2: Data Wrangling & Exploratory Analysis | Jarred | 2024-02-12 | Not Started
Update Readme with progress (week3-5) | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-01-29 | Not Started
Update Readme with progress | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete
Update Presentation Slides (week3-5) | Phase 1: Project Setup and Qualitative Research | Jingyi & Yinan | 2024-01-29 | Complete

## Weeks 1-3
Weeks 1 -3 01/23 - 2/06
Task | Phase | Team Lead | Due Date | Progress | Notes
Kickoff & Meeting Minutes | Phase 1: Project Setup and Qualitative Research | Team | 2024-01-29 | Complete
Project Management Plan | Phase 1: Project Setup and Qualitative Research | Jarred & Kathleen | 2024-01-29 | Complete
Project Schedule: Gant Chart | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete
Project Setup: Github Repo | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-01-29 | Complete
Research & Summary: Boone 2030 Plan | Phase 1: Project Setup and Qualitative Research | Jingyi | 2024-02-12 | In Progress
Research & Summary: Development Ordinances | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | In Progress
Research & Summary: Demographics | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-02-12 | In Progress
Research & Summary: Socio-economic Change | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | In Progress
Research & Summary: Story of Affordability | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | In Progress
Research & Summary:NC LIHTC Allocation Plan | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | In Progress
Research & Summary: "Workforce" Housing Programs | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | In Progress
Gather Open Data | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | In Progress
Update Readme with progress | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete
Update Presentation Slides | Phase 1: Project Setup and Qualitative Research | Jingyi & Yinan | 2024-01-29 | Complete
Update for all data wrangling

## Weeks 3-6
Weeks 3-5 2/06 - 02/13
Task | Phase | Team Lead | Due Date | Progress | Notes
Chris Quattro Meeting & Minutes | Phase 2: Data Wrangling & Exploratory Analysis | Team | 2024-02-13 | In Progress
Data Wrangling: Septic Permit Web Scraping | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-01-30
Data Wrangling:Septic Permit Analysis | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12
Data Wrangling: Exiting Data (From Folder) | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-01-29
Data Wrangling: Sold Property Characteristics | Phase 2: Data Wrangling & Exploratory Analysis | Jingyi | 2024-02-12
Use Case & Exploratory Analysis Write Up | Phase 2: Data Wrangling & Exploratory Analysis | Jarred & Kathleen | 2024-02-12
Research & Summary: Socio-economic Change | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12
Research & Summary: Story of Affordability | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12
Research & Summary: "Workforce" Housing Programs | Phase 2: Data Wrangling & Exploratory Analysis | Jarred | 2024-02-12
Gather Open Data | Phase 2: Data Wrangling & Exploratory Analysis | Jarred | 2024-02-12
Update Readme with progress | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-01-29
Research & Summary: "Workforce" Housing Programs | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | In Progress
Gather Open Data | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | In Progress
Update Readme with progress | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete
Update Presentation Slides | Phase 1: Project Setup and Qualitative Research | Jingyi & Yinan | 2024-01-29 | Complete
Weeks 3-5 2/06 - 02/13
Task | Phase | Team Lead | Due Date | Progress | Notes
Chris Quattro Meeting & Minutes | Phase 2: Data Wrangling & Exploratory Analysis | Team | 2024-02-13 | In Progress
Data Wrangling: Septic Permit Web Scraping | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-01-29
Data Wrangling:Septic Permit Analysis | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12
Data Wrangling: Exiting Data (From Folder) | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-01-29
Data Wrangling: Sold Property Characteristics | Phase 2: Data Wrangling & Exploratory Analysis | Jingyi | 2024-02-12
Use Case & Exploratory Analysis Write Up | Phase 2: Data Wrangling & Exploratory Analysis | Jarred & Kathleen | 2024-02-12
Research & Summary: Socio-economic Change | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12
Research & Summary: Story of Affordability | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12
Research & Summary: "Workforce" Housing Programs | Phase 2: Data Wrangling & Exploratory Analysis | Jarred | 2024-02-12
Gather Open Data | Phase 2: Data Wrangling & Exploratory Analysis | Jarred | 2024-02-12
Update Readme with progress | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-01-29