## Master List
Master Project Task List
Task | Phase | Team Lead | Due Date | Progress | Notes
Kickoff & Meeting Minutes | Phase 1: Project Setup and Qualitative Research | Team | 2024-01-29 | Complete
Project Management Plan | Phase 1: Project Setup and Qualitative Research | Jarred & Kathleen | 2024-01-29 | Complete
Project Schedule: Gant Chart | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete
Project Setup: Github Repo | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-01-29 | Complete
Update Readme with progress (week1-3) | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete | Slides?
Update Presentation Slides (week1-3) | Phase 1: Project Setup and Qualitative Research | Jingyi & Yinan | 2024-01-29 | Complete | Slides?
Update Readme with progress (week3-5) | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-01-29 | Complete | Slides?
Update Readme with progress | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete | Slides?
Update Presentation Slides (week3-5) | Phase 1: Project Setup and Qualitative Research | Jingyi & Yinan | 2024-01-29 | Complete | Slides?
Chris Quattro Meeting & Minutes | Phase 2: Data Wrangling & Exploratory Analysis | Team | 2024-01-31 | Complete | Slides?
Research & Summary: Boone 2030 Plan | Phase 1: Project Setup and Qualitative Research | Jingyi | 2024-02-12 | Complete | Slides?
Research & Summary: Development Ordinances | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | Complete | Slides?
Research & Summary: Demographics | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-02-12 | Complete | Slides?
Research & Summary: Socio-economic Change | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | Complete | Slides?
Research & Summary: Story of Affordability | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | Complete | Slides?
Research & Summary:NC LIHTC Allocation Plan | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | Complete | Slides?
Research & Summary: "Workforce" Housing Programs & surrounding context | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | Complete | Slides?
Gather Open Data | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | Complete | Slides?
Data Wrangling: Septic Permit Web Scraping | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12 | Complete | Slides?
Data Wrangling: Physiucal Landscape | Phase 2: Data Wrangling & Exploratory Analysis | Jingyi | 2024-02-12 | Complete | Slides?
Data Wrangling: Municipal & Legal Lines | Phase 2: Data Wrangling & Exploratory Analysis | Jarred | 2024-02-12 | Complete | Slides?
Data Wrangling: Inventory of Built Environment | Phase 2: Data Wrangling & Exploratory Analysis | Alice | 2024-02-12 | Complete | Slides?
Data Wrangling: Demographics | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-02-12 | Complete | Slides?
Use Case & Exploratory Analysis Write Up | Phase 2: Data Wrangling & Exploratory Analysis | Jarred & Kathleen | 2024-02-12 | Not Started
Gather Open Data | Phase 2: Data Wrangling & Exploratory Analysis | Everyone | 2024-02-12 | Complete
Presentation outline | Phase 3: Exploratory analysis and Presentation 1 | Everyone | 2024-02-12 | Complete
Data Wrangling: Soil and Water table | Phase 3: Exploratory analysis and Presentation 1 | Everyone | 2024-02-20 | In progress
Exploratory analysis and markdown: Problem Statement + Use case | Phase 3: Exploratory analysis and Presentation 1 | Jarred | 2024-02-23 | In progress
Exploratory analysis and markdown: Stakeholders and funding options | Phase 3: Exploratory analysis and Presentation 1 | Jarred | 2024-02-23 | In progress
Exploratory analysis and markdown: Area contrext (Housing, demographics, housing) | Phase 3: Exploratory analysis and Presentation 1 | Kathleen | 2024-02-23 | In progress
Exploratory analysis and markdown: Correlation Matrix & maps | Phase 3: Exploratory analysis and Presentation 1 | Yinan | 2024-02-23 | In progress
Exploratory analysis and markdown: Correlation Matrix & maps | Phase 3: Exploratory analysis and Presentation 1 | Gingyi | 2024-02-23 | In progress
Exploratory analysis and markdown: any additional maps and graphics | Phase 3: Exploratory analysis and Presentation 1 | Everyone | 2024-02-23 | In progress | Discuss on 02/20/23
Presentatiuon one Markdown - Exploratory Analysis | Phase 3: Exploratory analysis and Presentation 1 | ? | 2024-02-23 | In progress
Slides: Presentation 1 | Phase 3: Exploratory analysis and Presentation 1 | Alice

## Weeks 1-3
Weeks 1 -3 01/23 - 2/06
Task | Phase | Team Lead | Due Date | Progress | Notes
Kickoff & Meeting Minutes | Phase 1: Project Setup and Qualitative Research | Team | 2024-01-29 | Complete | 0
Project Management Plan | Phase 1: Project Setup and Qualitative Research | Jarred & Kathleen | 2024-01-29 | Complete | 0
Project Schedule: Gant Chart | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete | 0
Project Setup: Github Repo | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-01-29 | Complete | 0
Update Readme with progress (week1-3) | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete | Slides?
Update Presentation Slides (week1-3) | Phase 1: Project Setup and Qualitative Research | Jingyi & Yinan | 2024-01-29 | Complete | Slides?
Update Readme with progress (week3-5) | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-01-29 | Complete | Slides?
Update Readme with progress | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete | Slides?
Update Presentation Slides (week3-5) | Phase 1: Project Setup and Qualitative Research | Jingyi & Yinan | 2024-01-29 | Complete | Slides?
Chris Quattro Meeting & Minutes | Phase 2: Data Wrangling & Exploratory Analysis | Team | 2024-01-31 | Complete | Slides?
Research & Summary: Boone 2030 Plan | Phase 1: Project Setup and Qualitative Research | Jingyi | 2024-02-12 | Complete | Slides?
Research & Summary: Development Ordinances | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | Complete | Slides?
Research & Summary: Demographics | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-02-12 | Complete | Slides?
Research & Summary: Socio-economic Change | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | Complete | Slides?
Research & Summary: Story of Affordability | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | Complete | Slides?
Research & Summary:NC LIHTC Allocation Plan | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | Complete | Slides?
Research & Summary: "Workforce" Housing Programs & surrounding context | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | Complete | Slides?
Gather Open Data | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | Complete | Slides?
Data Wrangling: Septic Permit Web Scraping | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12 | Complete | Slides?
Data Wrangling: Physiucal Landscape | Phase 2: Data Wrangling & Exploratory Analysis | Jingyi | 2024-02-12 | Complete | Slides?
Data Wrangling: Municipal & Legal Lines | Phase 2: Data Wrangling & Exploratory Analysis | Jarred | 2024-02-12 | Complete | Slides?
Data Wrangling: Inventory of Built Environment | Phase 2: Data Wrangling & Exploratory Analysis | Alice | 2024-02-12 | Complete | Slides?
Data Wrangling: Demographics | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-02-12 | Complete | Slides?
Use Case & Exploratory Analysis Write Up | Phase 2: Data Wrangling & Exploratory Analysis | Jarred & Kathleen | 2024-02-12 | Not Started | 0
Gather Open Data | Phase 2: Data Wrangling & Exploratory Analysis | Everyone | 2024-02-12 | Complete | 0
Kickoff & Meeting Minutes | Phase 1: Project Setup and Qualitative Research | Team | 2024-01-29 | Complete
Project Management Plan | Phase 1: Project Setup and Qualitative Research | Jarred & Kathleen | 2024-01-29 | Complete
Project Schedule: Gant Chart | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete
Project Setup: Github Repo | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-01-29 | Complete
Research & Summary: Boone 2030 Plan | Phase 1: Project Setup and Qualitative Research | Jingyi | 2024-02-12 | In Progress
Research & Summary: Development Ordinances | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | In Progress
Research & Summary: Demographics | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-02-12 | In Progress
Research & Summary: Socio-economic Change | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | In Progress
Research & Summary: Story of Affordability | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | In Progress
Research & Summary:NC LIHTC Allocation Plan | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | In Progress
Research & Summary: "Workforce" Housing Programs | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | In Progress
Gather Open Data | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | In Progress
Update Readme with progress | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-01-29 | Complete
Update Presentation Slides | Phase 1: Project Setup and Qualitative Research | Jingyi & Yinan | 2024-01-29 | Complete

## Weeks 3-6
Weeks 3 -6 02/06 - 2/20
Task | Phase | Team Lead | Due Date | Progress | Notes
Research & Summary: Boone 2030 Plan | Phase 1: Project Setup and Qualitative Research | Jingyi | 2024-02-12 | Complete | Slides?
Research & Summary: Development Ordinances | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | Complete | Slides?
Research & Summary: Demographics | Phase 1: Project Setup and Qualitative Research | Kathleen | 2024-02-12 | Complete | Slides?
Research & Summary: Socio-economic Change | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | Complete | Slides?
Research & Summary: Story of Affordability | Phase 1: Project Setup and Qualitative Research | Yinan | 2024-02-12 | Complete | Slides?
Research & Summary:NC LIHTC Allocation Plan | Phase 1: Project Setup and Qualitative Research | Alice | 2024-02-12 | Complete | Slides?
Research & Summary: "Workforce" Housing Programs & surrounding context | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | Complete | Slides?
Gather Open Data | Phase 1: Project Setup and Qualitative Research | Jarred | 2024-02-12 | Complete | Slides?
Data Wrangling: Septic Permit Web Scraping | Phase 2: Data Wrangling & Exploratory Analysis | Yinan | 2024-02-12 | Complete | Slides?
Data Wrangling: Physiucal Landscape | Phase 2: Data Wrangling & Exploratory Analysis | Jingyi | 2024-02-12 | Complete | Slides?
Data Wrangling: Municipal & Legal Lines | Phase 2: Data Wrangling & Exploratory Analysis | Jarred | 2024-02-12 | Complete | Slides?
Data Wrangling: Inventory of Built Environment | Phase 2: Data Wrangling & Exploratory Analysis | Alice | 2024-02-12 | Complete | Slides?
Data Wrangling: Demographics | Phase 2: Data Wrangling & Exploratory Analysis | Kathleen | 2024-02-12 | Complete | Slides?
Data Wrangling: Soil and Water table | Phase 3: Exploratory analysis and Presentation 1 | Everyone | 2024-02-20 | In progress | 0
Exploratory analysis and markdown: Problem Statement + Use case | Phase 3: Exploratory analysis and Presentation 1 | Jarred | 2024-02-23 | In progress | 0
Exploratory analysis and markdown: Stakeholders and funding options | Phase 3: Exploratory analysis and Presentation 1 | Jarred | 2024-02-23 | In progress | 0
Exploratory analysis and markdown: Area contrext (Housing, demographics, housing) | Phase 3: Exploratory analysis and Presentation 1 | Kathleen | 2024-02-23 | In progress | 0
Exploratory analysis and markdown: Correlation Matrix & maps | Phase 3: Exploratory analysis and Presentation 1 | Yinan | 2024-02-23 | In progress | 0
Exploratory analysis and markdown: Correlation Matrix & maps | Phase 3: Exploratory analysis and Presentation 1 | Gingyi | 2024-02-23 | In progress | 0
Exploratory analysis and markdown: any additional maps and graphics | Phase 3: Exploratory analysis and Presentation 1 | Everyone | 2024-02-23 | In progress | Discuss on 02/20/23
Presentatiuon one Markdown - Exploratory Analysis | Phase 3: Exploratory analysis and Presentation 1 | ? | 2024-02-23 | In progress | 0
Slides: Presentation 1 | Phase 3: Exploratory analysis and Presentation 1 | Alice | 0 | 0 | 0